Scope of Work

Team Member(s): Rylee Renner

Date submitted for review: February 3, 2026

Submitted to: Civil and Environmental Engineering Department faculty

Project Goals

Per a Request for Proposal (RFP) from UNMC Water, Climate, and Health, this project will develop an analysis of air quality in Nebraska. The client has requested four analyses: (1) determination of the five Nebraska locations where the mean and median values of VOC, PM 2.5, and PM 10.0 are the highest, (2) analyses of when and where the maximums occurred and any potential reason why, (3) if humidity and temperature affect air quality, and (4) determination of any Air Quality Index (AQI) health risks based on the EPA’s AQI ratings at any of the Nebraska locations for PM 2.5 and PM 10.0.

Project Tasks

The following tasks will be required of the professional engineering team to complete the project goals.

Task 1: Determine the five Nebraska locations with highest VOC, PM 2.5, and PM 10.0 concentrations

Utilizing the AirPurple dataset, the data will be imported and organized in a Python environment. The CSV file will be loaded and structured into a DataFrame for analysis. To support pollutant summaries based on location, the data will be grouped by location, using the sensor coordinate data. Using standard statistical aggregation methods, the mean and median of the concentrations of VOC, PM 2.5, and PM 10.0 will be calculated. The statistical summary output will be sorted in descending order to identify the five Nebraska locations with the highest concentration of each pollutant. If necessary, the coordinates may need to be cross-referenced with mapping tools to determine the locations in terms of city names. As a result of this task, the top five Nebraska locations with the highest mean and median concentrations of each of the three pollutants will be reported, along with the processed data.

Task 2: Locate peak pollutant levels across Nebraska and assess possible causes

To identify the date and location of the maximum pollutant levels, the dataset will be analyzed to determine the highest concentration of VOC, PM 2.5, and PM 10.0 across all locations. After separating the maximum values, the date and location will be determined. The coordinates may need to be cross-referenced with mapping tools to determine the city the events took place in. A review of environmental and weather-related conditions on the determined dates will be conducted to provide potential explanations for the high pollutant levels in those locations. As a result of this task, the dates, locations, and reasons behind the maximum levels of PM 2.5, PM 10.0, and VOC will be reported.

Task 3: Assess how humidity and temperature relate to pollutant concentrations

To determine whether humidity and temperature affect Nebraska air quality, the data will first be categorized based on the specified ranges. Humidity values will be categorized into low, high, and very high humidity and temperatures will be grouped into below freezing, cool, warm, and hot categories. The data will then be grouped based on these categories and the mean concentrations of PM 2.5, PM 10.0, and VOC for each category will be calculated. These statistical summaries will aid in identifying patterns of pollutant levels across different humidity and temperature conditions. To support data interpretation, brief research on atmospheric processes and seasonal conditions in Nebraska may be necessary. This task will aid in determination of whether humidity and temperature play a role in air quality, supported by statistical summaries.

Task 4: Determine AQI exceedances, document timing and location, and research potential influences

Based on the EPA’s Air Quality Index (AQI) ratings, the dataset will be analyzed to determine any health risks at any location for PM 2.5 and PM 10.0. Thresholds corresponding to the AQI will be applied to identify unsafe pollutant levels. Associated dates and locations will be extracted to find when any issues occurred. Additional research will be done to determine safe values of PM 2.5 and PM 10.0 based on the AQI. Analyzing potential reasons for any unsafe levels will be necessary. This task will result in the determination of any unsafe PM 2.5 and PM 10.0 levels, the location of this occurrence, and reasoning behind it.

Task 5: Determine if altitude impacts air quality

The dataset will be analyzed to identify how the concentrations of PM 2.5, PM 10.0, and VOC vary with sensor altitude. Sensor readings will be filtered by the sensor altitude and the pollutant values for each location will be aggregated to compute the mean of each contaminant. A summary table will be formed to determine observable trends between air quality and altitude. This task will result in a clear summary of pollutant concentrations in different altitudes.

Project Deliverables

Summarized in the table below are the deliverables and their corresponding due dates.